## Sheet1
Task Name | Duration | Start | Finish | Resource Names
PFM Project | 113 days? | Wed 8/8/12 | Thu 12/27/12
Initiating | 21 days | Wed 8/8/12 | Wed 9/5/12
Register Capstone Project | 8 days | Wed 8/8/12 | Fri 8/17/12
Kick off meetings | 10 days | Thu 8/23/12 | Wed 9/5/12
Planing | 4 days? | Wed 9/5/12 | Mon 9/10/12
Develop Project Plan | 4 days? | Wed 9/5/12 | Mon 9/10/12
Project Plan Approve | 1 day? | Mon 9/10/12 | Mon 9/10/12
Excuting | 90 days? | Mon 9/10/12 | Thu 12/27/12
Analysis | 4 days | Mon 9/10/12 | Thu 9/13/12
Write Requirement | 4 days | Mon 9/10/12 | Thu 9/13/12 | LinhLLL,GamNT
Expenditure management function | 15 days? | Mon 9/10/12 | Tue 9/25/12
Coding (Input manually) | 7 days? | Mon 9/10/12 | Mon 9/17/12 | TUANNA
Coding (Input using NFC) | 12 days? | Mon 9/10/12 | Sat 9/22/12 | LOCND
Create Software Requirement Specification (SRS) document | 12 days? | Mon 9/10/12 | Sat 9/22/12 | LinhLLL,GamNT
Create Software Design Description (SDD) document (Input manually) | 2 days | Wed 9/19/12 | Thu 9/20/12 | TUANNA
Create Software Design Description (SDD) document (Input using NFC) | 3 days | Sun 9/23/12 | Tue 9/25/12 | LOCND
Write system test case | 8 days | Tue 9/18/12 | Tue 9/25/12 | KHANHLTM
Income management function | 10 days | Fri 9/21/12 | Mon 10/1/12
Coding | 8 days | Fri 9/21/12 | Fri 9/28/12 | TUANNA
Update Software Requirement Specification (SRS) document | 6 days | Sun 9/23/12 | Fri 9/28/12 | LinhLLL,GamNT
Update Software Design Description (SDD) document | 2 days | Sat 9/29/12 | Mon 10/1/12 | TUANNA
Write system test case | 2 days | Sat 9/29/12 | Mon 10/1/12 | KHANHLTM
Borrowing and lending management fuction | 9 days? | Tue 10/2/12 | Fri 10/12/12
Coding (Borrowing money function) | 6 days? | Tue 10/2/12 | Tue 10/9/12
Coding (Lending money management) | 6 days? | Tue 10/2/12 | Tue 10/9/12
Update Software Requirement Specification (SRS) document | 6 days? | Tue 10/2/12 | Tue 10/9/12
Update Software Design Description (SDD) document (Borrowing money function) | 3 days? | Wed 10/10/12 | Fri 10/12/12
Update Software Design Description (SDD) document (Lending money function) | 3 days? | Wed 10/10/12 | Fri 10/12/12
Write system test case | 1 day? | Fri 10/12/12 | Fri 10/12/12
Report function | 10 days? | Sat 10/13/12 | Tue 10/23/12
Coding | 7 days? | Sat 10/13/12 | Sat 10/20/12
Update Software Requirement Specification (SRS) document | 7 days? | Sat 10/13/12 | Sat 10/20/12
Update Software Design Description (SDD) document | 3 days? | Sun 10/21/12 | Tue 10/23/12
Write system test case | 3 days? | Sun 10/21/12 | Tue 10/23/12
Warning function | 10 days? | Sat 10/13/12 | Tue 10/23/12
Coding | 7 days? | Sat 10/13/12 | Sat 10/20/12
Update Software Requirement Specification (SRS) document | 7 days? | Sat 10/13/12 | Sat 10/20/12
Update Software Design Description (SDD) document | 3 days? | Sun 10/21/12 | Tue 10/23/12
Write system test case | 3 days? | Sun 10/21/12 | Tue 10/23/12
Sychronize function | 16 days? | Wed 10/24/12 | Mon 11/12/12
Coding (Mobile) | 14 days? | Wed 10/24/12 | Fri 11/9/12
Coding (Server) | 14 days? | Wed 10/24/12 | Fri 11/9/12
Update Software Requirement Specification (SRS) document | 14 days? | Wed 10/24/12 | Fri 11/9/12
Update Software Design Description (SDD) document (Mobile) | 2 days? | Sat 11/10/12 | Mon 11/12/12
Update Software Design Description (SDD) document (Server) | 2 days? | Sat 11/10/12 | Mon 11/12/12
Write system test case | 2 days? | Sat 11/10/12 | Mon 11/12/12
Using NFC for payment fuction | 14 days? | Tue 11/13/12 | Fri 11/30/12
Coding | 11 days? | Tue 11/13/12 | Tue 11/27/12 | LOCND
Update Software Requirement Specification (SRS) document | 11 days? | Tue 11/13/12 | Tue 11/27/12 | LinhLLL,GamNT
Update Software Design Description (SDD) document | 3 days? | Wed 11/28/12 | Fri 11/30/12 | LOCND
Write system test case | 3 days? | Wed 11/28/12 | Fri 11/30/12 | KHANHLTM
Barcode function | 14 days? | Tue 11/13/12 | Fri 11/30/12
Coding | 11 days? | Tue 11/13/12 | Tue 11/27/12 | TUANNA
Update Software Requirement Specification (SRS) document | 11 days? | Tue 11/13/12 | Tue 11/27/12 | LinhLLL,GamNT
Update Software Design Description (SDD) document | 3 days? | Wed 11/28/12 | Fri 11/30/12 | TUANNA
Write system test case | 3 days? | Wed 11/28/12 | Fri 11/30/12 | KHANHLTM
System implemented | 3 days? | Sat 12/1/12 | Tue 12/4/12 | TUANNA,LOCND
Testing | 7 days? | Wed 12/5/12 | Wed 12/12/12
Execute system test | 3 days? | Wed 12/5/12 | Fri 12/7/12 | PFM Team
Create Software Test Documentation (STD) document | 4 days | Sat 12/8/12 | Wed 12/12/12 | KHANHLTM
Update Software Design Description (SDD) document (System Design) | 7 days? | Wed 12/5/12 | Wed 12/12/12 | GamNT,LinhLLL
Update Software Design Description (SDD) document (Design Database) | 7 days? | Wed 12/5/12 | Wed 12/12/12 | TUANNA,LOCND
Create Software User Mannual (SUM) document | 7 days | Wed 12/5/12 | Wed 12/12/12 | KHANHLTM
Create final report | 6 days? | Thu 12/13/12 | Thu 12/20/12 | LinhLLL,GamNT,KHANHLTM
Closing | 4 days | Mon 12/24/12 | Thu 12/27/12
Prepare final project presentation | 3 days | Mon 12/24/12 | Wed 12/26/12 | PFM Team
Project presentation | 3 hrs | Thu 12/27/12 | Thu 12/27/12 | PFM Team
Project completed | 1 day | Thu 12/27/12 | Thu 12/27/12