## Sheet1
Task Name | Duration | Start | Finish | Predecessors | Resource Names
PFM Project | 120 days | Wed 8/5/12 | Thu 12/27/12
1. Initiation | 7 days | Wed 8/1/12 | Wed 8/8/12
1.1 Research information | 3 days | Wed 8/1/12 | Fri 8/3/12 |  | PFM Team
1.2 Identify Project | 2 days | Fri 8/3/12 | Sun 8/5/12 |  | PFM Team
1.3 Approve Project | 2 days | Mon 8/6/12 | Tue 8/7/12 |  | PFM Team
1.4 Register Capstone Project | 1 day | Tue 8/7/12 | Wed 8/8/12 |  | TuanNA
1.5 Kick off meetings | 1 day | Tue 8/7/12 | Wed 8/8/12 |  | PFM Team
2. Plan | 23 days | Thu 8/9/12 | Sat 9/1/12
2.1 Research project requirement | 5 days | Thu 8/9/12 | Mon 8/13/12 |  | PFM Team
2.2 Create application main function | 7 days | Mon 8/13/12 | Mon 8/20/12 |  | PFM Team
2.3 Define project scope | 3 days | Mon 8/20/12 | Thu 8/23/12 |  | PFM Team
2.4 Study technical | 5 days | Thu 8/23/12 | Tue 8/28/12 |  | PFM Team
2.5 Set up work environment | 3 days | Tue 8/28/12 | Sat 9/1/12 |  | LocND, TuanNA
3. Executing
3.1 Sprint 0 | 15 days | Sat 9/1/12 | Sat 9/15/12
3.1.1 Create SRS document | 10 days | Sat 9/1/12 | Mon 9/10/12 |  | GamNT, LinhLLL
3.1.2 Research Technical | 10 days | Mon 9/1/12 | Mon 9/10/12
3.1.2.1 Research SQLite | 5 days | Mon 9/1/12 | Wed 9/5/12 |  | TuanNA
3.1.2.2 Create SQLite sample | 5 days | Wed 9/5/12 | Mon 9/10/12 |  | TuanNA
3.1.2.3 Research Chart | 5 days | Mon 9/1/12 | Wed 9/5/12 |  | LocND
3.1.2.4 Create Chart sample | 5 days | Wed 9/5/12 | Mon 9/10/12 |  | LocND
3.1.3 Create simple GUI | 5 days | Mon 9/10/12 | Sat 9/15/12 |  | KhanhLTM, LinhLLL, GamNT
3.1.4 Update SRS | 5 days | Mon 9/10/12 | Sat 9/15/12 |  | GamNT, LinhLLL
3.1.5 Create Report 1(Introduction) | 5 days | Mon 9/10/12 | Sat 9/15/12
3.2 Sprint 1( Schedule & Borrowing & Lending function) | 15 days | Sat 9/15/12 | Sun 9/30/12
3.2.1 Update Use case | 8 days | Sat 9/15/12 | Sun 9/23/12 |  | LinhLLL
3.2.2 Update Report 1 | 8 days | Sat 9/15/12 | Sun 9/23/12 |  | GamNT
3.2.3 Summit and Review simple GUI | 0 day | Mon 9/16/12 | Mon 9/16/12 |  | Mr. HienNV, PFM Team
3.2.3.1 Simple GUI | 0 day | Mon 9/16/12 | Mon 9/16/12 |  | Mr. HienNV, PFM Team
3.2.3.2 Chart sample | 0 day | Mon 9/16/12 | Mon 9/16/12 |  | Mr. HienNV, PFM Team
3.2.3.3 SQLite sample | 0 day | Mon 9/16/12 | Mon 9/16/12 |  | Mr. HienNV, PFM Team
3.2.3.4 Report 1 | 0 day | Mon 9/16/12 | Mon 9/16/12 |  | Mr. HienNV, PFM Team
3.2.4 Create final GUI
3.2.4.1 Schedule | 9 days | Sat 9/15/12 | Sun 9/23/12
3.2.4.1.1 New schedule screen | 3 days | Sat 9/15/12 | Tue 9/18/12 |  | LinhLLL, KhanhLTM
3.2.4.1.2 View schedule screen | 3 days | Tue 9/18/12 | Thu 9/20/12 |  | LinhLLL, KhanhLTM
3.2.4.1.3 Schedule screen | 3 days | Thu 9/20/12 | Sun 9/23/12 |  | LinhLLL, KhanhLTM
3.2.4.2 Borrowing and Lending | 9 days | Sat 9/15/12 | Sun 9/23/12 |  | LinhLLL, KhanhLTM
3.2.4.2.1 New borrowing screen | 3 days | Sat 9/15/12 | Tue 9/18/12 |  | LinhLLL, KhanhLTM
3.2.4.2.2 View borrowing screen | 3 days | Tue 9/18/12 | Thu 9/20/12 |  | LinhLLL, KhanhLTM
3.2.4.1.3 Borrowing screen | 3 days | Thu 9/20/12 | Sun 9/23/12 |  | LinhLLL, KhanhLTM
3.2.5 Create System design | 7 days | Mon 9/17/12 | Sun 9/23/12
3.2.5.1 Create Database design | 7 days | Mon 9/17/12 | Sun 9/23/12 |  | TuanNA
3.2.5.2 Create System design | 7 days | Mon 9/17/12 | Sun 9/23/12 |  | LocND
3.2.6 Coding
3.2.6.1 Schedule funtion ( Input screen) | 3 days | Thu 9/20/12 | Sun 9/23/12 |  | LocND
3.2.6.2 Borrowing and Lending function (Input screen) | 3 days | Thu 9/20/12 | Sun 9/23/12 |  | TuanNA
3.2.7 Summit and Review | 0 day | Mon 9/24/12 | Mon 9/24/12
3.2.7.1 Use case diagram | 0 day | Mon 9/24/12 | Mon 9/24/12 |  | Mr. HienNV, PFM Team
3.2.7.2 Report 1 (ver 0.1) | 0 day | Mon 9/24/12 | Mon 9/24/12 |  | Mr. HienNV, PFM Team
3.2.7.3 System design | 0 day | Mon 9/24/12 | Mon 9/24/12 |  | Mr. HienNV, PFM Team
3.2.7.4 Database design | 0 day | Mon 9/24/12 | Mon 9/24/12 |  | Mr. HienNV, PFM Team
3.2.7.4 Final GUI(ver 0.1) | 0 day | Mon 9/24/12 | Mon 9/24/12 |  | Mr. HienNV, PFM Team
3.2.7.5 Schedule funtion ( Input screen) | 0 day | Mon 9/24/12 | Mon 9/24/12 |  | Mr. HienNV, PFM Team
3.2.7.6 Borrowing and Lending function (Input screen) | 0 day | Mon 9/24/12 | Mon 9/24/12 |  | Mr. HienNV, PFM Team
3.2.8 Update Report 1 | 7 days | Mon 9/24/12 | Mon 10/1/12 |  | GamNT
3.2.9 Update SRS | 7 days | Mon 9/24/12 | Mon 10/1/12 |  | GamNT, LinhLLL
3.2.10 Update Final GUI ( release) | 7 days | Mon 9/24/12 | Mon 10/1/12 |  | LinhLLL
3.2.11 Update System design | 7 days | Mon 9/24/12 | Mon 10/1/12
3.2.11.1 Update Database design | 7 days | Mon 9/24/12 | Mon 10/1/12 |  | TuanNA
3.2.11.2 Update System design | 7 days | Mon 9/24/12 | Mon 10/1/12 |  | LocND
3.2.11.3 Create detail database design | 7 days | Mon 9/24/12 | Mon 10/1/12 |  | TuanNA
3.2.11.4 Create detail system design | 7 days | Mon 9/24/12 | Mon 10/1/12 |  | LocND
3.2.12 Coding | 7 days | Mon 9/24/12 | Mon 10/1/12
3.2.12.1 Schedule function (all screen) | 5 days | Mon 9/24/12 | Thu 9/27/12 |  | LocND
3.2.12.1.1 Execute unit test of Schedule function | 1 days | Thu 9/27/12 | Thu 9/27/12 |  | LocND
3.2.12.2 Borrowing and Lending function (all screen) | 5 days | Mon 9/24/12 | Thu 9/27/12 |  | TuanNA
3.2.12.1.1 Execute unit test of Borrowing and Lending function | 1 days | Thu 9/27/12 | Thu 9/27/12 |  | TuanNA
3.2.12.3 Intergrate Schedule and Borrowing & Lending function
3.2.13 Prepare slide for the project assessment | 1 days | Tue 9/25/12 | Tue 9/25/12 |  | LinhLLL, TuanNA
3.2.14 Create testcase for Schedule, Borrowing and Lending function | 2 days | Thu 9/27/12 | Sat 9/29/12 |  | KhanhLTM
3.2.15 Research | 2 days | Wed 9/26/12 | Thu 9/27/12
3.2.15.1 QR code | 1 day | Wed 9/26/12 | Wed 9/26/12 |  | LocND
3.2.15.2 NFC code | 1 day | Thu 9/27/12 | Thu 9/27/12 |  | LocND
3.2.15 Create research report | 2 days | Wed 9/26/12 | Thu 9/27/12 |  | LocND
3.2.16 Create detail function information document | 1 day | Thu 9/27/12 | Thu 9/27/12 |  | GamNT
3.2.17 Release Schedule, Borrowing and Lending function | 0 day | Thu 9/27/12 | Thu 9/27/12 |  | LocND,TuanNA
3.2.18 Execute test | 2 days | Fri 9/28/12 | Sat 9/29/12 |  | KhanhLTM
3.2.19 Complete test round 1 | 0 day | Sat 9/29/12 | Sat 9/29/12 |  | KhanhLTM
3.2.20 Fix bugs of Schedule, Borrowing and Lending function | 1 day | Sun 9/30/12 | Sun 9/30/12 |  | TuanNA, LocND
3.2.21 Execute test round 2 | 1 day | Sun 9/30/12 | Sun 9/30/12
3.2.22 Review Schedule, Borrowing and Lending function | 0 day | Mon 10/1/12 | Mon 10/1/12
3.2.23 Meeting for complete sprint 1 | 0 day | Mon 10/1/12 | Mon 10/1/12
3.3 Sprint 2 ( Income and Expense management) | 15 days | Mon 10/1/12 | Mon 10/15/12
3.3.1 Update Use case | 2 days | Mon 10/1/12 | Wed 10/3/12 |  | LinhLLL
3.3.2 Create GUI of Income and Expense management screen (ver 0.1) | 4 days | Mon 10/1/12 | Fri 10/5/12 |  | LinhLLL, KhanhLTM
3.3.2.1 Main screen of function | 1 day | Mon 10/1/12 | Tue 10/2/12 |  | LinhLLL, KhanhLTM
3.3.2.2 View detail income and expense screen | 1 day | Tue 10/2/12 | Wed 10/3/12 |  | LinhLLL, KhanhLTM
3.3.2.3 Input income or expense screen | 1 day | Wed 10/3/12 | Thu 10/4/12 |  | LinhLLL, KhanhLTM
3.3.2.4 Edit income or expense screen | 1 day | Thu 10/4/12 | Thu 10/4/12 |  | LinhLLL, KhanhLTM
3.3.3 Update System design | 3 days | Mon 10/1/12 | Thu 10/4/12 |  | LocND, TuanNA
3.3.4 Create report 2 ( Plan) | 5 days | Mon 10/1/12 | Fri 10/5/12 |  | PFM Team
3.3.5 Coding | 10 days | Mon 10/1/12 | Thu 10/11/12 |  | TuanNA, LocND
3.3.5.1 Use QR code to input expense | 10 days | Mon 10/1/12 | Thu 10/11/12 |  | LocND
3.3.5.2 Use NFC to input expense | 10 days | Mon 10/1/12 | Thu 10/11/12 |  | TuanNA
3.3.6 Create test case for sprint 2 | 3 days | Fri 10/5/12 | Mon 10/8/12 |  | KhanhLTM
3.3.7 Summit and Review | 0 day | Mon 10/8/12 | Mon 10/8/12 |  | Mr. HienNV, PFM Team
3.3.7.1 Report 2 (ver 0.1) | 0 day | Mon 10/8/12 | Mon 10/8/12 |  | Mr. HienNV, PFM Team
3.3.7.2 Coding | 0 day | Mon 10/8/12 | Mon 10/8/12 |  | Mr. HienNV, PFM Team
3.3.7.3 GUI | 0 day | Mon 10/8/12 | Mon 10/8/12 |  | Mr. HienNV, PFM Team
3.3.8 Update GUI (final) | 1 day | Mon 10/8/12 | Tue 10/9/12
3.3.9 Execute test round 1 | 2 days | Fri 10/12/12 | Sat 10/13/12 |  | KhanhLTM
3.3.10 Fix bugs | 1 day | Sat 10/13/12 | Sun 10/14/12 |  | TuanNA, LocND
3.3.11 Execute test round 2 | 1 day | Sat 10/13/12 | Sun 10/14/12 |  | KhanhLTM
3.3.12 Review Income and Expense management function | 0 day | Mon 10/15/12 | Mon 10/15/12 |  | Mr. HienNV, PFM Team
3.3.13 Meeting for complete sprint 2 | 0 day | Mon 10/15/12 | Mon 10/15/12 |  | Mr. HienNV, PFM Team
3.4 Sprint 3 ( Report and Warning function) | 15 days | Mon 10/1/12 | Mon 10/15/12
3.3.1 Update Use case
3.3.2 Create GUI of Report and Warning function (Draff)
3.3.2.1 Report function
3.3.2.1.1 Main screen
3.3.2.1.2 Detail screen
3.3.2.1.3 Chart
3.3.2.2 Warning function
3.3.2.2.1 Main screen
3.3.2.2.2 Setup screen
3.3.2.3 Warning screen
3.3.3 Update System design
3.3.4 Update Report 2 (plan)
3.3.5 Coding
3.3.5.1 Use QR code to input expense
3.3.5.2 Use NFC to input expense
3.3.6 Create test case for sprint 2
3.3.7 Summit and Review
3.3.7.1 Report 2
3.3.7.2 Coding
3.3.7.3 GUI
3.3.8 Execute test round 1
3.3.9 Fix bugs
3.3.10 Execute test round 2
3.3.11 Review Income and Expense management function
3.3.12 Meeting for complete sprint 2