## Sheet1
Task Name | Start | Finish | Resource Names
PFM Project | Wed 8/8/12 | Thu 12/27/12
Initiating | Wed 8/8/12 | Wed 9/5/12
Register Capstone Project | Wed 8/8/12 | Fri 8/17/12
Kick off meetings | Thu 8/23/12 | Wed 9/5/12
Planing | Wed 9/5/12 | Mon 9/10/12
Develop Project Plan | Wed 9/5/12 | Mon 9/10/12
Project Plan Approve | Mon 9/10/12 | Mon 9/10/12
Excuting | Wed 9/5/12 | Tue 12/4/12
Analysis | Wed 9/5/12 | Mon 9/10/12
Write Requirement | Wed 9/5/12 | Mon 9/10/12 | LinhLLL,GamNT
Schedule, Borrowing and lending management fuction | Mon 9/10/12 | Tue 9/25/12
Design UI | Mon 9/10/12 | Wed 9/12/12 | TUANNA
Coding | Thu 9/13/12 | Sat 9/22/12 | LOCND
Update UI | Thu 9/13/12 | Sat 9/22/12 | LinhLLL,GamNT
Create Software Requirement Specification (SRS) document | Thu 9/20/12 | Sat 9/22/12 | TUANNA
Create Software Design Description (SDD) document | Sun 9/23/12 | Tue 9/25/12 | LOCND
Write system test case | Sun 9/23/12 | Tue 9/25/12 | KHANHLTM
Expenditure and Income management fuction | Wed 9/26/12 | Thu 10/11/12
Design UI | Wed 9/26/12 | Fri 9/28/12 | TUANNA
Coding | Sat 9/29/12 | Mon 10/8/12 | LinhLLL,GamNT
Update UI | Sat 9/29/12 | Mon 10/8/12 | TUANNA
Create Software Requirement Specification (SRS) document | Tue 10/9/12 | Thu 10/11/12 | KHANHLTM
Create Software Design Description (SDD) document | Tue 10/9/12 | Thu 10/11/12
Write system test case | Tue 10/9/12 | Thu 10/11/12
Report and Warning fuction | Fri 10/12/12 | Sat 10/27/12
Design UI | Fri 10/12/12 | Sun 10/14/12
Coding | Mon 10/15/12 | Wed 10/24/12
Update UI | Mon 10/15/12 | Wed 10/24/12
Create Software Requirement Specification (SRS) document | Thu 10/25/12 | Sat 10/27/12
Create Software Design Description (SDD) document | Thu 10/25/12 | Sat 10/27/12
Write system test case | Thu 10/25/12 | Sat 10/27/12
Sychronize function | Sun 10/28/12 | Mon 11/12/12
Design UI | Sun 10/28/12 | Tue 10/30/12
Coding | Wed 10/31/12 | Fri 11/9/12
Update UI | Wed 10/31/12 | Fri 11/9/12
Update Software Requirement Specification (SRS) document | Sat 11/10/12 | Mon 11/12/12
Update Software Design Description (SDD) document | Sat 11/10/12 | Mon 11/12/12
Write system test case | Sat 11/10/12 | Mon 11/12/12
Using NFC for payment fuction | Mon 11/12/12 | Fri 11/30/12
Coding | Mon 11/12/12 | Tue 11/27/12
Update Software Requirement Specification (SRS) document | Wed 11/28/12 | Fri 11/30/12
Update Software Design Description (SDD) document | Wed 11/28/12 | Fri 11/30/12
Write system test case | Wed 11/28/12 | Fri 11/30/12
Barcode function | Mon 11/12/12 | Fri 11/30/12
Coding | Mon 11/12/12 | Tue 11/27/12
Update Software Requirement Specification (SRS) document | Wed 11/28/12 | Fri 11/30/12
Update Software Design Description (SDD) document | Wed 11/28/12 | Fri 11/30/12
Write system test case | Wed 11/28/12 | Fri 11/30/12 | LOCND
System implemented | Sat 12/1/12 | Tue 12/4/12 | LinhLLL,GamNT
Testing | Wed 12/5/12 | Wed 12/12/12 | LOCND
Execute system test | Wed 12/5/12 | Fri 12/7/12 | KHANHLTM
Create Software Test Documentation (STD) document | Sat 12/8/12 | Wed 12/12/12
Pre-Closing | Thu 12/13/12 | Sun 12/23/12 | TUANNA
Update Software Design Description (SDD) document (System Design) | Thu 12/13/12 | Tue 12/18/12 | LinhLLL,GamNT
Update Software Design Description (SDD) document (Design Database) | Thu 12/13/12 | Tue 12/18/12 | TUANNA
Create Software User Mannual (SUM) document | Thu 12/13/12 | Tue 12/18/12 | KHANHLTM
Create final report | Wed 12/19/12 | Sun 12/23/12 | TUANNA,LOCND
Closing | Mon 12/24/12 | Thu 12/27/12
Prepare final project presentation | Mon 12/24/12 | Wed 12/26/12 | PFM Team
Project presentation | Thu 12/27/12 | Thu 12/27/12 | KHANHLTM
Project completed | Thu 12/27/12 | Thu 12/27/12 | GamNT,LinhLLL
Update Software Design Description (SDD) document (Design Database) | Wed 12/5/12 | Wed 12/12/12 | TUANNA,LOCND
Create Software User Mannual (SUM) document | Wed 12/5/12 | Wed 12/12/12 | KHANHLTM
Create final report | Thu 12/13/12 | Thu 12/20/12 | LinhLLL,GamNT,KHANHLTM
Closing | Mon 12/24/12 | Thu 12/27/12
Prepare final project presentation | Mon 12/24/12 | Wed 12/26/12 | PFM Team
Project presentation | Thu 12/27/12 | Thu 12/27/12 | PFM Team
Project completed | Thu 12/27/12 | Thu 12/27/12