## Sheet1
Task Name | Duration | Start | Finish | Predecessors | Resource Names
PFM Project | 120 days | Wed 8/5/12 | Thu 12/27/12
1. Initiation | 7 days | Wed 8/1/12 | Wed 8/8/12
1.1 Research information | 3 days | Wed 8/1/12 | Fri 8/3/12 |  | PFM Team
1.2 Identify Project | 2 days | Fri 8/3/12 | Sun 8/5/12 |  | PFM Team
1.3 Approve Project | 2 days | Mon 8/6/12 | Tue 8/7/12 |  | PFM Team
1.4 Register Capstone Project | 1 day | Tue 8/7/12 | Wed 8/8/12 |  | TuanNA
1.5 Kick off meetings | 1 day | Tue 8/7/12 | Wed 8/8/12 |  | PFM Team
2. Plan | 23 days | Thu 8/9/12 | Sat 9/1/12
2.1 Research project requirement | 5 days | Thu 8/9/12 | Mon 8/13/12 |  | PFM Team
2.2 Create application main function | 7 days | Mon 8/13/12 | Mon 8/20/12 |  | PFM Team
2.3 Define project scope | 3 days | Mon 8/20/12 | Thu 8/23/12 |  | PFM Team
2.4 Study technical | 5 days | Thu 8/23/12 | Tue 8/28/12 |  | PFM Team
2.5 Set up work environment | 3 days | Tue 8/28/12 | Sat 9/1/12 |  | LocND, TuanNA
3. Executing
3.1 Sprint 0 | 15 days | Sat 9/1/12 | Sat 9/15/12
3.1.1 Create report 3 (SRS document) | 10 days | Sat 9/1/12 | Mon 9/10/12 |  | GamNT, LinhLLL
3.1.2 Research Technical | 10 days | Mon 9/1/12 | Mon 9/10/12
3.1.2.1 Research SQLite | 5 days | Mon 9/1/12 | Wed 9/5/12 |  | TuanNA
3.1.2.2 Create SQLite sample | 5 days | Wed 9/5/12 | Mon 9/10/12 |  | TuanNA
3.1.2.3 Research Chart | 5 days | Mon 9/1/12 | Wed 9/5/12 |  | LocND
3.1.2.4 Create Chart sample | 5 days | Wed 9/5/12 | Mon 9/10/12 |  | LocND
3.1.3 Create simple GUI | 5 days | Mon 9/10/12 | Sat 9/15/12 |  | KhanhLTM, LinhLLL, GamNT
3.1.4 Update SRS | 5 days | Mon 9/10/12 | Sat 9/15/12 |  | GamNT, LinhLLL
3.1.5 Create Report 1(Introduction) | 5 days | Mon 9/10/12 | Sat 9/15/12
3.2 Sprint 1( Schedule & Borrowing & Lending function) | 15 days | Sat 9/15/12 | Sun 9/30/12
3.2.1 Update Use case | 8 days | Sat 9/15/12 | Sun 9/23/12 |  | LinhLLL
3.2.2 Update Report 1 | 8 days | Sat 9/15/12 | Sun 9/23/12 |  | GamNT
3.2.3 Summit and Review simple GUI | 0 day | Mon 9/16/12 | Mon 9/16/12 |  | Mr. HienNV, PFM Team
3.2.3.1 Simple GUI | 0 day | Mon 9/16/12 | Mon 9/16/12 |  | Mr. HienNV, PFM Team
3.2.3.2 Chart sample | 0 day | Mon 9/16/12 | Mon 9/16/12 |  | Mr. HienNV, PFM Team
3.2.3.3 SQLite sample | 0 day | Mon 9/16/12 | Mon 9/16/12 |  | Mr. HienNV, PFM Team
3.2.3.4 Report 1 | 0 day | Mon 9/16/12 | Mon 9/16/12 |  | Mr. HienNV, PFM Team
3.2.4 Create final GUI (ver 0.1)
3.2.4.1 Schedule | 9 days | Sat 9/15/12 | Sun 9/23/12
3.2.4.1.1 New schedule screen | 3 days | Sat 9/15/12 | Tue 9/18/12 |  | LinhLLL, KhanhLTM
3.2.4.1.2 View schedule screen | 3 days | Tue 9/18/12 | Thu 9/20/12 |  | LinhLLL, KhanhLTM
3.2.4.1.3 Schedule screen | 3 days | Thu 9/20/12 | Sun 9/23/12 |  | LinhLLL, KhanhLTM
3.2.4.2 Borrowing and Lending | 9 days | Sat 9/15/12 | Sun 9/23/12 |  | LinhLLL, KhanhLTM
3.2.4.2.1 New borrowing screen | 3 days | Sat 9/15/12 | Tue 9/18/12 |  | LinhLLL, KhanhLTM
3.2.4.2.2 View borrowing screen | 3 days | Tue 9/18/12 | Thu 9/20/12 |  | LinhLLL, KhanhLTM
3.2.4.1.3 Borrowing screen | 3 days | Thu 9/20/12 | Sun 9/23/12 |  | LinhLLL, KhanhLTM
3.2.5 Create Report 4 (System design) | 7 days | Mon 9/17/12 | Sun 9/23/12
3.2.5.1 Create Database design | 7 days | Mon 9/17/12 | Sun 9/23/12 |  | TuanNA
3.2.5.2 Create System design | 7 days | Mon 9/17/12 | Sun 9/23/12 |  | LocND
3.2.6 Coding
3.2.6.1 Schedule funtion ( Input screen) | 3 days | Thu 9/20/12 | Sun 9/23/12 |  | LocND
3.2.6.2 Borrowing and Lending function (Input screen) | 3 days | Thu 9/20/12 | Sun 9/23/12 |  | TuanNA
3.2.7 Summit and Review | 0 day | Mon 9/24/12 | Mon 9/24/12
3.2.7.1 Use case diagram | 0 day | Mon 9/24/12 | Mon 9/24/12 |  | Mr. HienNV, PFM Team
3.2.7.2 Report 1 (ver 0.1) | 0 day | Mon 9/24/12 | Mon 9/24/12 |  | Mr. HienNV, PFM Team
3.2.7.3 System design | 0 day | Mon 9/24/12 | Mon 9/24/12 |  | Mr. HienNV, PFM Team
3.2.7.4 Database design | 0 day | Mon 9/24/12 | Mon 9/24/12 |  | Mr. HienNV, PFM Team
3.2.7.4 Final GUI(ver 0.1) | 0 day | Mon 9/24/12 | Mon 9/24/12 |  | Mr. HienNV, PFM Team
3.2.7.5 Schedule funtion ( Input screen) | 0 day | Mon 9/24/12 | Mon 9/24/12 |  | Mr. HienNV, PFM Team
3.2.7.6 Borrowing and Lending function (Input screen) | 0 day | Mon 9/24/12 | Mon 9/24/12 |  | Mr. HienNV, PFM Team
3.2.8 Update Report 1 | 7 days | Mon 9/24/12 | Mon 10/1/12 |  | GamNT
3.2.9 Update SRS | 7 days | Mon 9/24/12 | Mon 10/1/12 |  | GamNT, LinhLLL
3.2.10 Update Final GUI ( release) | 7 days | Mon 9/24/12 | Mon 10/1/12 |  | LinhLLL
3.2.11 Update System design | 7 days | Mon 9/24/12 | Mon 10/1/12
3.2.11.1 Update Database design | 7 days | Mon 9/24/12 | Mon 10/1/12 |  | TuanNA
3.2.11.2 Update System design | 7 days | Mon 9/24/12 | Mon 10/1/12 |  | LocND
3.2.11.3 Create detail database design | 7 days | Mon 9/24/12 | Mon 10/1/12 |  | TuanNA
3.2.11.4 Create detail system design | 7 days | Mon 9/24/12 | Mon 10/1/12 |  | LocND
3.2.12 Coding | 7 days | Mon 9/24/12 | Mon 10/1/12
3.2.12.1 Schedule function (all screen) | 5 days | Mon 9/24/12 | Thu 9/27/12 |  | LocND
3.2.12.1.1 Execute unit test of Schedule function | 1 days | Thu 9/27/12 | Thu 9/27/12 |  | LocND
3.2.12.2 Borrowing and Lending function (all screen) | 5 days | Mon 9/24/12 | Thu 9/27/12 |  | TuanNA
3.2.12.1.1 Execute unit test of Borrowing and Lending function | 1 days | Thu 9/27/12 | Thu 9/27/12 |  | TuanNA
3.2.12.3 Intergrate Schedule and Borrowing & Lending function
3.2.13 Prepare slide for the project assessment | 1 days | Tue 9/25/12 | Tue 9/25/12 |  | LinhLLL, TuanNA
3.2.14 Create testcase for Schedule, Borrowing and Lending function | 2 days | Thu 9/27/12 | Sat 9/29/12 |  | KhanhLTM
3.2.15 Research | 2 days | Wed 9/26/12 | Thu 9/27/12
3.2.15.1 QR code | 1 day | Wed 9/26/12 | Wed 9/26/12 |  | LocND
3.2.15.2 NFC code | 1 day | Thu 9/27/12 | Thu 9/27/12 |  | LocND
3.2.15 Create research report | 2 days | Wed 9/26/12 | Thu 9/27/12 |  | LocND
3.2.16 Create detail function information document | 1 day | Thu 9/27/12 | Thu 9/27/12 |  | GamNT
3.2.17 Release Schedule, Borrowing and Lending function | 0 day | Thu 9/27/12 | Thu 9/27/12 |  | LocND,TuanNA
3.2.18 Execute test | 2 days | Fri 9/28/12 | Sat 9/29/12 |  | KhanhLTM
3.2.19 Complete test round 1 | 0 day | Sat 9/29/12 | Sat 9/29/12 |  | KhanhLTM
3.2.20 Fix bugs of Schedule, Borrowing and Lending function | 1 day | Sun 9/30/12 | Sun 9/30/12 |  | TuanNA, LocND
3.2.21 Execute test round 2 | 1 day | Sun 9/30/12 | Sun 9/30/12
3.2.22 Review Schedule, Borrowing and Lending function | 0 day | Mon 10/1/12 | Mon 10/1/12
3.2.23 Meeting for complete sprint 1 | 0 day | Mon 10/1/12 | Mon 10/1/12
3.3 Sprint 2 ( Income and Expense management, Warning) | 15 days | Mon 10/1/12 | Thu 10/18/12
3.3.1 Update Use case | 2 days | Mon 10/1/12 | Wed 10/3/12 |  | LinhLLL
3.3.2 Create GUI for Sprint 2 (ver 0.1) | 4 days | Mon 10/1/12 | Fri 10/5/12 |  | LinhLLL
3.3.2.1 Income and Expense management | 3 days | Mon 10/1/12 | Thu 10/4/12 |  | LinhLLL
3.3.2.1 Main screen | 1 day | Mon 10/1/12 | Tue 10/2/12 |  | LinhLLL
3.3.2.2 View detail income and expense screen | 1 day | Tue 10/2/12 | Wed 10/3/12 |  | LinhLLL
3.3.2.3 Input income or expense screen | 1 day | Wed 10/3/12 | Thu 10/4/12 |  | LinhLLL
3.3.2.4 Edit income or expense screen | 1 day | Thu 10/4/12 | Thu 10/4/12 |  | LinhLLL
3.3.2.2 Warning | 1 day | Thu 10/4/12 | Fri 10/5/12 |  | LinhLLL
3.3.3 Update System design | 3 days | Mon 10/1/12 | Thu 10/4/12 |  | LocND, TuanNA
3.3.4 Create report 2 ( Plan) | 5 days | Mon 10/1/12 | Fri 10/5/12 |  | PFM Team
3.3.5 Coding | 10 days | Mon 10/1/12 | Thu 10/11/12 |  | TuanNA, LocND
3.3.5.1 Income and Expense management | 10 days | Thu 10/4/12 | Sun 10/14/12 |  | TuanNA
3.3.5.2 Warning | 10 days | Thu 10/4/12 | Sun 10/14/12 |  | LocND
3.3.6 Create test case for sprint 2 | 3 days | Fri 10/5/12 | Mon 10/8/12 |  | KhanhLTM
3.3.7 Summit and Review | 0 day | Mon 10/8/12 | Mon 10/8/12 |  | Mr. HienNV, PFM Team
3.3.7.1 Report 2 | 0 day | Mon 10/8/12 | Mon 10/8/12 |  | Mr. HienNV, PFM Team
3.3.7.2 Coding | 0 day | Mon 10/8/12 | Mon 10/8/12 |  | Mr. HienNV, PFM Team
3.3.7.3 GUI | 0 day | Mon 10/8/12 | Mon 10/8/12 |  | Mr. HienNV, PFM Team
3.3.7.4 Test case | 0 day | Mon 10/8/12 | Mon 10/8/12 |  | Mr. HienNV, PFM Team
3.3.8 Update GUI (final) | 1 day | Mon 10/8/12 | Tue 10/9/12 |  | LinhLLL
3.3.9 Execute test round 1 | 3 days | Mon 10/8/12 | Thu 10/11/12 |  | KhanhLTM, LinhLLL, GamNT
3.3.10 Fix bugs | 3 day | Sun 10/14/12 | Wed 10/17/12 |  | TuanNA, LocND
3.3.11 Execute test round 2 | 1 day | Wed 10/17/12 | Thu 10/18/12 |  | KhanhLTM, LinhLLL, GamNT
3.3.12 Review Income and Expense management, warning functions | 0 day | Thu 10/18/12 | Thu 10/18/12 |  | Mr. HienNV, PFM Team
3.3.13 Meeting for complete sprint 2 | 0 day | Thu 10/18/12 | Thu 10/18/12 |  | Mr. HienNV, PFM Team
3.4 Sprint 3 ( NFC and QR Code) | 15 days | Thu 10/18/12 | Sun 11/04/12
3.3.1 Update Use case | 1 day | Thu 10/18/12 | Fri 10/19/12 |  | LinhLLL
3.3.2 Create GUI (ver 0.1) | 2 days | Thu 10/18/12 | Sat 10/20/12 |  | LinhLLL
3.3.2.1 NFC | 2 days | Thu 10/18/12 | Sat 10/20/12 |  | LinhLLL
3.3.2.2 QR code | 2 days | Thu 10/18/12 | Sat 10/20/12 |  | LinhLLL
3.3.3 Update System design | 2 days | Thu 10/18/12 | Sat 10/20/12 |  | LocND, TuanNA
3.3.4 Update report 2 ( Plan) | 2 days | Thu 10/18/12 | Sat 10/20/12 |  | LinhLLL, GamNT
3.3.5 Coding | 10 days | Thu 10/18/12 | Sun 10/28/12 |  | LocND, TuanNA
3.3.5.1 Use QR code to input expense | 10 days | Thu 10/18/12 | Sun 10/28/12 |  | TuanNA
3.3.5.2 Use NFC to input expense | 10 days | Thu 10/18/12 | Sun 10/28/12 |  | LocND
3.3.6 Create test case for sprint 3 | 3 days | Sat 10/20/12 | Sun 10/28/12 |  | KhanhLTM
3.3.7 Summit and Review | 0 day | Mon 10/29/12 | Mon 10/29/12 |  | Mr. HienNV, PFM Team
3.3.7.1 Report 2 (final) | 0 day | Mon 10/29/12 | Mon 10/29/12 |  | Mr. HienNV, PFM Team
3.3.7.2 Coding | 0 day | Mon 10/29/12 | Mon 10/29/12 |  | Mr. HienNV, PFM Team
3.3.7.3 GUI | 0 day | Mon 10/29/12 | Mon 10/29/12 |  | Mr. HienNV, PFM Team
3.3.7.4 Test case | 0 day | Mon 10/29/12 | Mon 10/29/12 |  | Mr. HienNV, PFM Team
3.3.8 Execute test round 1 | 3 days | Mon 10/29/12 | Thu 11/1/12 |  | KhanhLTM, LinhLLL, GamNT
3.3.9 Fix bugs | 3 days | Mon 10/30/12 | Thu 11/1/12 |  | LocND, TuanNA
3.3.10 Execute test round 2 | 1 day | Fri 11/2/12 | Sat 11/3/12 |  | KhanhLTM, LinhLLL, GamNT
3.3.11 Review NFC and QR code | 0 day | Mon 11/4/12 | Mon 11/4/12 |  | Mr. HienNV, PFM Team
3.3.12 Meeting for complete sprint 3 | 0 day | Mon 11/4/12 | Mon 11/4/12 |  | Mr. HienNV, PFM Team
3.4 Sprint 4 ( Report and Synchronize function) | 15 days | Mon 11/4/12 | Mon 11/19/12
3.4.1 Update Use case | 1 day | Mon 11/4/12 | Tue 11/5/12 |  | LinhLLL
3.4.2 Create GUI of Synchronize function (ver 0.1) | 5 days | Mon 11/4/12 | Sat 11/9/12 |  | LinhLLL
3.4.2.1 Synchronize function | 2 days | Mon 11/4/12 | Wed 11/6/12 |  | LinhLLL
3.4.2.1.1 Client | 1 day | Mon 11/4/12 | Tue 11/5/12 |  | LinhLLL
3.4.2.1.2 Server | 1 day | Tue 11/5/12 | Wed 11/6/12 |  | LinhLLL
3.4.2.2 Report function | 3 days | Wed 11/6/12 | Sat 11/9/12 |  | LinhLLL
3.4.2.2.1 Report detail | 2 days | Wed 11/6/12 | Fri 11/8/12 |  | LinhLLL
3.4.2.2.2 Chart | 1 day | Fri 11/8/12 | Sat 11/9/12 |  | LinhLLL
3.4.3 Update System design | 2 days | Mon 11/4/12 | Wed 11/6/12 |  | LocND, TuanNA
3.4.4 Update SRS(ver 0.2) | 2 days | Mon 11/4/12 | Wed 11/6/12 |  | GamNT
3.4.5 Coding | 12 days | Wed 11/6/12 | Sun 11/18/12 |  | LocND, TuanNA
3.4.5.1 Report | 12 days | Wed 11/6/12 | Sun 11/18/12 |  | LocND
3.4.5.1.1 Report detail | 6 days | Wed 11/6/12 | Mon 11/12/12 |  | LocND
3.4.5.1.2 Chart | 6 days | Mon 11/12/12 | Sun 11/18/12 |  | LocND
3.4.5.2 Synchronize | 12 days | Wed 11/6/12 | Sun 11/18/12 |  | TuanNA
3.4.5.2.1 Client | 6 days | Wed 11/6/12 | Mon 11/12/12 |  | TuanNA
3.4.5.2.2 Server | 6 days | Mon 11/12/12 | Sun 11/18/12 |  | TuanNA
3.4.6 Create test case for sprint 4 | 3 days | Mon 11/12/12 | Thu 11/15/12 |  | KhanhLTM
3.4.7 Summit and Review | 0 day | Mon 11/12/12 | Mon 11/12/12 |  | Mr. HienNV, PFM Team
3.4.7.1 Report 3 (ver 0.1) | 0 day | Mon 11/12/12 | Mon 11/12/12 |  | Mr. HienNV, PFM Team
3.4.7.2 Coding | 0 day | Mon 11/12/12 | Mon 11/12/12 |  | Mr. HienNV, PFM Team
3.4.7.3 GUI | 0 day | Mon 11/12/12 | Mon 11/12/12 |  | Mr. HienNV, PFM Team
3.4.7.4 Test case | 0 day | Mon 11/12/12 | Mon 11/12/12 |  | Mr. HienNV, PFM Team
3.4.8 Execute test round 1 | 5 days | Sat 11/10/12 | Thu 11/15/12 |  | KhanhLTM
3.4.9 Fix bugs | 2 days | Thu 11/15/12 | Sat 11/17/12 |  | LocND, TuanNA
3.4.10 Execute test round 2 | 2 days | Sat 11/17/12 | Mon 11/19/12 |  | KhanhLTM, LinhLLL, GamNT
3.4.11 Review Report and Synchronize function | 0 day | Mon 11/19/12 | Mon 11/19/12 |  | Mr. HienNV, PFM Team
3.4.12 Meeting for complete sprint 4 | 0 day | Mon 11/19/12 | Mon 11/19/12 |  | Mr. HienNV, PFM Team
4. System implement | 7 days | Mon 11/19/12 | Mon 11/26/12 |  | LocND, TuanNA
4.1 Intergrate 4 main functions | 7 days | Mon 11/19/12 | Mon 11/26/12 |  | LocND, TuanNA
4.2 Update report 3 (ver 0.2) | 3 days | Mon 11/19/12 | Wed 11/22/12 |  | GamNT, LinhLLL
4.3 Create report 4 (ver 0.1) | 3 days | Mon 11/19/12 | Wed 11/22/12 |  | LocND, TuanNA
4.5 Update all functions GUI (ver 0.1) | 5 days | Mon 11/19/12 | Fri 11/24/12 |  | LinhLLL, KhanhLTM
4.6 Summit and review | 0 day | Mon 11/26/12 | Mon 11/26/12 |  | Mr. HienNV, PFM Team
4.6.1 Coding | 0 day | Mon 11/26/12 | Mon 11/26/12 |  | Mr. HienNV, PFM Team
4.6.2 Report 3 | 0 day | Mon 11/26/12 | Mon 11/26/12 |  | Mr. HienNV, PFM Team
4.6.3 Report 4 | 0 day | Mon 11/26/12 | Mon 11/26/12 |  | Mr. HienNV, PFM Team
5. System test | 7 days | Mon 11/26/12 | Mon 12/3/12
5.1 Create