## Sheet1
Task Name | Duration | Start | Finish | Predecessors | Resource Names
PFM Project | 120 days? | Wed 8/8/12 | Thu 12/27/12
Initiating | 21 days | Wed 8/8/12 | Wed 9/5/12
Register Capstone Project | 8 days | Wed 8/8/12 | Fri 8/17/12 |  | TUANNA
Kick off meetings | 10 days | Thu 8/23/12 | Wed 9/5/12 |  | PFM Team
Planing | 4 days? | Wed 9/5/12 | Mon 9/10/12
Develop Project Plan | 4 days? | Wed 9/5/12 | Mon 9/10/12 |  | PFM Team
Project Plan Approve | 1 day? | Mon 9/10/12 | Mon 9/10/12 |  | PFM Team
Excuting | 81 days? | Wed 9/5/12 | Tue 12/4/12
Analysis | 9 days? | Wed 9/5/12 | Sat 9/15/12
Write Requirement | 4 days | Wed 9/5/12 | Mon 9/10/12 |  | LinhLLL,GamNT
Design UI for sprint 1 | 5 days? | Tue 9/11/12 | Sat 9/15/12 | 9 | LinhLLL,GamNT,KHANHLTM
Make database design | 5 days? | Tue 9/11/12 | Sat 9/15/12 |  | TUANNA
Make system design | 5 days? | Tue 9/11/12 | Sat 9/15/12 |  | LOCND
Update detail plan | 5 days? | Tue 9/11/12 | Sat 9/15/12 |  | TUANNA
Make report 1 | 5 days? | Tue 9/11/12 | Sat 9/15/12 |  | GamNT
Schedule, Borrowing and lending management fuction | 15 days? | Sun 9/16/12 | Sun 9/30/12
Coding (Schdule function) | 12 days? | Sun 9/16/12 | Thu 9/27/12 |  | TUANNA
Coding (Borrowing and lending function) | 12 days | Sun 9/16/12 | Thu 9/27/12 |  | LOCND
Update UI for sprint 1 | 12 days | Sun 9/16/12 | Thu 9/27/12 |  | KHANHLTM,LinhLLL,GamNT
Create UI for sprint 2 | 12 days? | Sun 9/16/12 | Thu 9/27/12 |  | KHANHLTM,LinhLLL,GamNT
Create Software Requirement Specification (SRS) document | 3 days? | Fri 9/28/12 | Sun 9/30/12 |  | LinhLLL,GamNT
Create Software Design Description (SDD) document - Schedule function | 3 days | Fri 9/28/12 | Sun 9/30/12 | 16 | TUANNA
Create Software Design Description (SDD) document - Borrowing and lending function | 3 days | Fri 9/28/12 | Sun 9/30/12 |  | LOCND
Write system test case | 3 days | Fri 9/28/12 | Sun 9/30/12 |  | KHANHLTM
Expenditure and Income management fuction | 13 days? | Mon 10/1/12 | Mon 10/15/12
Coding (Expenditure management function) | 10 days | Mon 10/1/12 | Fri 10/12/12 |  | LOCND
Coding (Income function) | 10 days? | Mon 10/1/12 | Fri 10/12/12 |  | TUANNA
Update UI for sprint 2 | 10 days | Mon 10/1/12 | Fri 10/12/12 |  | KHANHLTM,LinhLLL,GamNT
Create UI for sprint 3 | 10 days | Mon 10/1/12 | Fri 10/12/12 |  | KHANHLTM,LinhLLL,GamNT
Create Software Requirement Specification (SRS) document | 3 days | Sat 10/13/12 | Mon 10/15/12 | 25 | LinhLLL,GamNT
Create Software Design Description (SDD) document - Expenditure management function | 3 days | Sat 10/13/12 | Mon 10/15/12 | 25 | LOCND
Create Software Design Description (SDD) document - Income funtione | 3 days | Sat 10/13/12 | Mon 10/15/12 |  | TUANNA
Write system test case | 3 days | Sat 10/13/12 | Mon 10/15/12 | 25 | KHANHLTM
Report and Warning fuction | 15 days | Tue 10/16/12 | Tue 10/30/12
Coding (Report function) | 12 days | Tue 10/16/12 | Sat 10/27/12 |  | LOCND
Coding (Warning function) | 12 days | Tue 10/16/12 | Sat 10/27/12 |  | TUANNA
Update UI for spint 3 | 12 days | Tue 10/16/12 | Sat 10/27/12 |  | KHANHLTM,LinhLLL,GamNT
Create UI for sprint 4 | 12 days | Tue 10/16/12 | Sat 10/27/12 |  | KHANHLTM,LinhLLL,GamNT
Create Software Requirement Specification (SRS) document | 3 days | Sun 10/28/12 | Tue 10/30/12 | 35 | LinhLLL,GamNT
Create Software Design Description (SDD) document | 3 days | Sun 10/28/12 | Tue 10/30/12 | 35 | LOCND
Create Software Design Description (SDD) document | 3 days | Sun 10/28/12 | Tue 10/30/12 |  | TUANNA
Write system test case | 3 days | Sun 10/28/12 | Tue 10/30/12 | 35 | KHANHLTM
Sychronize function | 15 days? | Wed 10/31/12 | Fri 11/16/12
Coding (Mobile) | 12 days | Wed 10/31/12 | Tue 11/13/12 |  | LOCND
Coding (Server) | 12 days | Wed 10/31/12 | Tue 11/13/12 |  | TUANNA
Update UI | 12 days? | Wed 10/31/12 | Tue 11/13/12 |  | LinhLLL,GamNT,KHANHLTM
Update Software Requirement Specification (SRS) document | 3 days | Wed 11/14/12 | Fri 11/16/12 | 44 | LinhLLL,GamNT
Update Software Design Description (SDD) document - Mobile | 3 days | Wed 11/14/12 | Fri 11/16/12 | 44 | LOCND
Update Software Design Description (SDD) document - Server | 2 days | Wed 11/14/12 | Thu 11/15/12 |  | TUANNA
Write system test case | 2 days | Wed 11/14/12 | Thu 11/15/12 | 44 | KHANHLTM
Using NFC for payment fuction | 12 days? | Fri 11/16/12 | Fri 11/30/12
Coding | 9 days | Fri 11/16/12 | Tue 11/27/12 |  | LOCND
Update Software Requirement Specification (SRS) document | 3 days? | Wed 11/28/12 | Fri 11/30/12 | 51 | LinhLLL,GamNT
Update Software Design Description (SDD) document | 3 days? | Wed 11/28/12 | Fri 11/30/12 | 51 | LOCND
Write system test case | 3 days? | Wed 11/28/12 | Fri 11/30/12 | 51 | KHANHLTM
Barcode function | 12 days? | Fri 11/16/12 | Fri 11/30/12
Coding | 9 days? | Fri 11/16/12 | Tue 11/27/12 |  | TUANNA
Update Software Requirement Specification (SRS) document | 3 days? | Wed 11/28/12 | Fri 11/30/12 | 56 | LinhLLL,GamNT
Update Software Design Description (SDD) document | 3 days? | Wed 11/28/12 | Fri 11/30/12 | 56 | TUANNA
Write system test case | 3 days? | Wed 11/28/12 | Fri 11/30/12 | 56 | KHANHLTM
System implemented | 3 days? | Sat 12/1/12 | Tue 12/4/12 |  | TUANNA,LOCND
Testing | 7 days? | Wed 12/5/12 | Wed 12/12/12
Execute system test | 3 days? | Wed 12/5/12 | Fri 12/7/12 |  | PFM Team
Create Software Test Documentation (STD) document | 4 days | Sat 12/8/12 | Wed 12/12/12 | 62 | KHANHLTM
Pre-Closing | 8 days? | Thu 12/13/12 | Sun 12/23/12
Update Software Design Description (SDD) document (System Design) | 4 days? | Thu 12/13/12 | Tue 12/18/12 |  | GamNT,LinhLLL
Update Software Design Description (SDD) document (Design Database) | 4 days? | Thu 12/13/12 | Tue 12/18/12 |  | TUANNA,LOCND
Create Software User Mannual (SUM) document | 4 days | Thu 12/13/12 | Tue 12/18/12 |  | KHANHLTM
Create final report | 4 days? | Wed 12/19/12 | Sun 12/23/12 | 67 | LinhLLL,GamNT,KHANHLTM
Closing | 4 days | Mon 12/24/12 | Thu 12/27/12
Prepare final project presentation | 3 days | Mon 12/24/12 | Wed 12/26/12 |  | PFM Team
Project presentation | 3 hrs | Thu 12/27/12 | Thu 12/27/12 |  | PFM Team
Project completed | 1 day | Thu 12/27/12 | Thu 12/27/12 | 70 | PFM Team