## Sheet1
1. Test report
Project | PFM |  | Project manager |  | LinhLLL
Application | Money Tracker
Consolidated By | KhanhLTM |  | Reviewed By |  | GamNT
Last update date | 2012-12-24 |  | Reviewed date |  | 2012-12-25
Test Execution Summary
Reported by | Le Thi Minh Khanh
Date | 2012-12-24
| Pass | Fail | Untested | Accepted |  | N/A | Number of Test cases
Test Sprint 1_Pass 1 | 30 | 24 | 0 | 0 |  | 0 | 54
Function-Use case 1 | 20 | 11 | 0 | 0 |  | 0 | 31
Function-Use case 3 | 10 | 13 | 0 | 0 |  | 0 | 23
Test coverage
Test coverage | [6 empty] | 100%
Test successful coverage | [6 empty] | 55.55%
| Pass | Fail | Untested | Accepted |  | N/A | Number of Test cases
Test Sprint 1_Pass 2 | 54 | 0 | 0 | 0 |  | 0 | 54
Function-Use case 1 | 31 | 0 | 0 | 0 |  | 0 | 31
Function-Use case 3 | 23 | 0 | 0 | 0 |  | 0 | 23
Test coverage
Test coverage | [6 empty] | 100%
Test successful coverage | [6 empty] | 100%
| Pass | Fail | Untested | Accepted |  | N/A | Number of Test cases
Test Sprint 2_Pass 1 | 14 | 16 | 0 | 0 |  | 0 | 30
Function-Use case 2 | 8 | 10 | 0 | 0 |  | 0 | 18
Function-Use case 5 | 6 | 6 | 0 | 0 |  | 0 | 12
Test coverage
Test coverage | [6 empty] | 100%
Test successful coverage | [6 empty] | 46.66.%
| Pass | Fail | Untested | Accepted |  | N/A | Number of Test cases
Test Sprint 2_Pass 2 | 30 | 0 | 0 | 0 |  | 0 | 30
Function-Use case 2 | 18 | 0 | 0 | 0 |  | 0 | 18
Function-Use case 5 | 12 | 0 | 0 | 0 |  | 0 | 12
Test coverage
Test coverage | [6 empty] | 100%
Test successful coverage | [6 empty] | 100%
| Pass | Fail | Untested | Accepted |  | N/A | Number of Test cases
Test Sprint 3_Pass 1 | 3 | 3 | 0 | 0 |  | 0 | 6
Function-NFC tag_QR code | 3 | 3 | 0 | 0 |  | 0 | 6
Test coverage
Test coverage | [6 empty] | 100%
Test successful coverage | [6 empty] | 50%
| Pass | Fail | Untested | Accepted |  | N/A | Number of Test cases
Test Sprint 3_Pass 2 | 6 | 0 | 0 | 0 |  | 0 | 6
Function-NFC tag_QR code | 6 | 0 | 0 | 0 |  | 0 | 6
Test coverage
Test coverage | [6 empty] | 100%
Test successful coverage | [6 empty] | 100%
| Pass | Fail | Untested | Accepted |  | N/A | Number of Test cases
Test Sprint 4_Pass 1 | 5 | 7 | 0 | 0 |  | 0 | 12
Function-Use case 6 | 2 | 2 | 0 | 0 |  | 0 | 4
Function-Use case 4 | 3 | 5 | 0 | 0 |  | 0 | 8
Test coverage
Test coverage | [6 empty] | 100%
Test successful coverage | [6 empty] | 41.66%
| Pass | Fail | Untested | Accepted |  | N/A | Number of Test cases
Test Sprint 4_Pass 2 | 12 | 0 | 0 | 0 |  | 0 | 12
Function-Use case 6 | 4 | 0 | 0 | 0 |  | 0 | 4
Function-Use case 4 | 8 | 0 | 0 | 0 |  | 0 | 8
Test coverage
Test coverage | [6 empty] | 100%
Test successful coverage | [6 empty] | 100%
| Pass | Fail | Untested | Accepted |  | N/A | Number of Test cases
Test Sprint 5_Pass 1 | 4 | 0 | 0 | 0 |  | 0 | 4
Function-Use case 7 | 4 | 0 | 0 | 0 |  | 0 | 4
Test coverage
Test coverage | [6 empty] | 100%
Test successful coverage | [6 empty] | 100%