## Sheet1
Task Name | Duration | Start | Finish | Predecessors | Resource Names
PFM Project | 119 days? | Wed 8/8/12 | Thu 12/27/12
Initiating | 21 days | Wed 8/8/12 | Wed 9/5/12
Register Capstone Project | 8 days | Wed 8/8/12 | Fri 8/17/12 |  | TUANNA
Kick off meetings | 10 days | Thu 8/23/12 | Wed 9/5/12 |  | PFM Team
Planing | 4 days? | Wed 9/5/12 | Mon 9/10/12
Develop Project Plan | 4 days? | Wed 9/5/12 | Mon 9/10/12 |  | PFM Team
Project Plan Approve | 1 day? | Mon 9/10/12 | Mon 9/10/12 |  | PFM Team
Excuting | 80 days? | Wed 9/5/12 | Tue 12/4/12
Analysis | 4 days | Wed 9/5/12 | Mon 9/10/12
Write Requirement | 4 days | Wed 9/5/12 | Mon 9/10/12 |  | LinhLLL,GamNT
Schedule, Borrowing and lending management fuction | 15 days? | Mon 9/10/12 | Tue 9/25/12
Design UI | 3 days? | Mon 9/10/12 | Wed 9/12/12 |  | LinhLLL,GamNT,KHANHLTM
Coding | 9 days? | Thu 9/13/12 | Sat 9/22/12 | 11 | TUANNA,LOCND
Update UI | 9 days? | Thu 9/13/12 | Sat 9/22/12 | 11 | KHANHLTM,LinhLLL,GamNT
Create Software Requirement Specification (SRS) document | 3 days? | Thu 9/20/12 | Sat 9/22/12 |  | LinhLLL,GamNT
Create Software Design Description (SDD) document | 3 days | Sun 9/23/12 | Tue 9/25/12 | 12 | TUANNA,LOCND
Write system test case | 3 days | Sun 9/23/12 | Tue 9/25/12 |  | KHANHLTM
Expenditure and Income management fuction | 14 days? | Wed 9/26/12 | Thu 10/11/12
Design UI | 3 days? | Wed 9/26/12 | Fri 9/28/12 |  | LinhLLL,GamNT,KHANHLTM
Coding | 8 days | Sat 9/29/12 | Mon 10/8/12 | 18 | TUANNA,LOCND
Update UI | 8 days | Sat 9/29/12 | Mon 10/8/12 | 18 | KHANHLTM,LinhLLL,GamNT
Create Software Requirement Specification (SRS) document | 3 days | Tue 10/9/12 | Thu 10/11/12 | 19 | LinhLLL,GamNT
Create Software Design Description (SDD) document | 3 days | Tue 10/9/12 | Thu 10/11/12 | 19 | TUANNA,LOCND
Write system test case | 3 days | Tue 10/9/12 | Thu 10/11/12 | 19 | KHANHLTM
Report and Warning fuction | 16 days | Fri 10/12/12 | Sat 10/27/12
Design UI | 3 days | Fri 10/12/12 | Sun 10/14/12 |  | LinhLLL,GamNT,KHANHLTM
Coding | 10 days | Mon 10/15/12 | Wed 10/24/12 | 25 | TUANNA,LOCND
Update UI | 10 days | Mon 10/15/12 | Wed 10/24/12 | 25 | KHANHLTM,LinhLLL,GamNT
Create Software Requirement Specification (SRS) document | 3 days | Thu 10/25/12 | Sat 10/27/12 | 26 | LinhLLL,GamNT
Create Software Design Description (SDD) document | 3 days | Thu 10/25/12 | Sat 10/27/12 | 26 | TUANNA,LOCND
Write system test case | 3 days | Thu 10/25/12 | Sat 10/27/12 | 26 | KHANHLTM
Sychronize function | 14 days? | Sun 10/28/12 | Mon 11/12/12
Design UI | 3 days | Sun 10/28/12 | Tue 10/30/12 |  | LinhLLL,GamNT,KHANHLTM
Coding | 9 days | Wed 10/31/12 | Fri 11/9/12 | 32 | TUANNA,LOCND
Update UI | 9 days? | Wed 10/31/12 | Fri 11/9/12 | 32 | LinhLLL,GamNT,KHANHLTM
Update Software Requirement Specification (SRS) document | 2 days | Sat 11/10/12 | Mon 11/12/12 | 33 | LinhLLL,GamNT
Update Software Design Description (SDD) document | 2 days | Sat 11/10/12 | Mon 11/12/12 | 33 | TUANNA,LOCND
Write system test case | 2 days | Sat 11/10/12 | Mon 11/12/12 | 33 | KHANHLTM
Using NFC for payment fuction | 16 days? | Mon 11/12/12 | Fri 11/30/12
Coding | 13 days? | Mon 11/12/12 | Tue 11/27/12 |  | LOCND
Update Software Requirement Specification (SRS) document | 3 days? | Wed 11/28/12 | Fri 11/30/12 | 39 | LinhLLL,GamNT
Update Software Design Description (SDD) document | 3 days? | Wed 11/28/12 | Fri 11/30/12 | 39 | LOCND
Write system test case | 3 days? | Wed 11/28/12 | Fri 11/30/12 | 39 | KHANHLTM
Barcode function | 16 days? | Mon 11/12/12 | Fri 11/30/12
Coding | 13 days? | Mon 11/12/12 | Tue 11/27/12 |  | TUANNA
Update Software Requirement Specification (SRS) document | 3 days? | Wed 11/28/12 | Fri 11/30/12 | 44 | LinhLLL,GamNT
Update Software Design Description (SDD) document | 3 days? | Wed 11/28/12 | Fri 11/30/12 | 44 | TUANNA
Write system test case | 3 days? | Wed 11/28/12 | Fri 11/30/12 | 44 | KHANHLTM
System implemented | 3 days? | Sat 12/1/12 | Tue 12/4/12 |  | TUANNA,LOCND
Testing | 7 days? | Wed 12/5/12 | Wed 12/12/12
Execute system test | 3 days? | Wed 12/5/12 | Fri 12/7/12 |  | PFM Team
Create Software Test Documentation (STD) document | 4 days | Sat 12/8/12 | Wed 12/12/12 | 50 | KHANHLTM
Pre-Closing | 8 days? | Thu 12/13/12 | Sun 12/23/12
Update Software Design Description (SDD) document (System Design) | 4 days? | Thu 12/13/12 | Tue 12/18/12 |  | GamNT,LinhLLL
Update Software Design Description (SDD) document (Design Database) | 4 days? | Thu 12/13/12 | Tue 12/18/12 |  | TUANNA,LOCND
Create Software User Mannual (SUM) document | 4 days | Thu 12/13/12 | Tue 12/18/12 |  | KHANHLTM
Create final report | 4 days? | Wed 12/19/12 | Sun 12/23/12 | 55 | LinhLLL,GamNT,KHANHLTM
Closing | 4 days | Mon 12/24/12 | Thu 12/27/12
Prepare final project presentation | 3 days | Mon 12/24/12 | Wed 12/26/12 |  | PFM Team
Project presentation | 3 hrs | Thu 12/27/12 | Thu 12/27/12 |  | PFM Team
Project completed | 1 day | Thu 12/27/12 | Thu 12/27/12 | 58 | PFM Team