## Sheet1
Task Name | Duration | Start | Finish | Resource Names
PFM Project | 100 days | Wed 8/5/12 | Thu 12/7/12
1. Initiation | 7 days | Wed 8/1/12 | Wed 8/8/12
1.1 Research information | 3 days | Wed 8/1/12 | Fri 8/3/12 | PFM Team
1.2 Identify Project | 2 days | Fri 8/3/12 | Sun 8/5/12 | PFM Team
1.3 Approve Project | 2 days | Mon 8/6/12 | Tue 8/7/12 | PFM Team
1.4 Register Capstone Project | 1 day | Tue 8/7/12 | Wed 8/8/12 | TuanNA
1.5 Kick off meetings | 1 day | Tue 8/7/12 | Wed 8/8/12 | PFM Team
2. Plan | 23 days | Thu 8/9/12 | Sat 9/1/12
2.1 Research project requirement | 5 days | Thu 8/9/12 | Mon 8/13/12 | PFM Team
2.2 Create application main function | 7 days | Mon 8/13/12 | Mon 8/20/12 | PFM Team
2.3 Define project scope | 3 days | Mon 8/20/12 | Thu 8/23/12 | PFM Team
2.4 Study technic | 5 days | Thu 8/23/12 | Tue 8/28/12 | PFM Team
2.5 Set up work environment | 3 days | Tue 8/28/12 | Sat 9/1/12 | LocND, TuanNA
3. Executing
3.1 Sprint 0 | 15 days | Sat 9/1/12 | Sat 9/15/12
3.1.1 Create report 3 (SRS document) | 10 days | Sat 9/1/12 | Mon 9/10/12 | GamNT, LinhLLL
3.1.2 Research Technic | 10 days | Mon 9/1/12 | Mon 9/10/12
3.1.2.1 Research SQLite | 5 days | Mon 9/1/12 | Wed 9/5/12 | TuanNA
3.1.2.2 Create SQLite sample | 5 days | Wed 9/5/12 | Mon 9/10/12 | TuanNA
3.1.2.3 Research Chart | 5 days | Mon 9/1/12 | Wed 9/5/12 | LocND
3.1.2.4 Create Chart sample | 5 days | Wed 9/5/12 | Mon 9/10/12 | LocND
3.1.3 Create simple GUI | 5 days | Mon 9/10/12 | Sat 9/15/12 | KhanhLTM, LinhLLL, GamNT
3.1.4 Update SRS | 5 days | Mon 9/10/12 | Sat 9/15/12 | GamNT, LinhLLL
3.1.5 Create Report 1(Introduction) | 5 days | Mon 9/10/12 | Sat 9/15/12
3.2 Sprint 1( Schedule & Borrowing & Lending function) | 23 days | Sat 9/15/12 | Mon 10/8/12
3.2.1 Update Use case | 8 days | Sat 9/15/12 | Sun 9/23/12 | LinhLLL
3.2.2 Update Report 1 | 8 days | Sat 9/15/12 | Sun 9/23/12 | GamNT
3.2.3 Summit and Review simple GUI | 0 day | Mon 9/16/12 | Mon 9/16/12 | Mr. HienNV, PFM Team
3.2.3.1 Simple GUI | 0 day | Mon 9/16/12 | Mon 9/16/12 | Mr. HienNV, PFM Team
3.2.3.2 Chart sample | 0 day | Mon 9/16/12 | Mon 9/16/12 | Mr. HienNV, PFM Team
3.2.3.3 SQLite sample | 0 day | Mon 9/16/12 | Mon 9/16/12 | Mr. HienNV, PFM Team
3.2.3.4 Report 1 | 0 day | Mon 9/16/12 | Mon 9/16/12 | Mr. HienNV, PFM Team
3.2.4 Create final GUI (ver 0.1) | 9 days | Sat 9/15/12 | Sun 9/23/12 | LinhLLL, KhanhLTM
3.2.4.1 Schedule | 9 days | Sat 9/15/12 | Sun 9/23/12 | LinhLLL, KhanhLTM
3.2.4.1.1 New schedule screen | 3 days | Sat 9/15/12 | Tue 9/18/12 | LinhLLL, KhanhLTM
3.2.4.1.2 View schedule screen | 3 days | Tue 9/18/12 | Thu 9/20/12 | LinhLLL, KhanhLTM
3.2.4.1.3 Schedule screen | 3 days | Thu 9/20/12 | Sun 9/23/12 | LinhLLL, KhanhLTM
3.2.4.2 Borrowing and Lending | 9 days | Sat 9/15/12 | Sun 9/23/12 | LinhLLL, KhanhLTM
3.2.4.2.1 New borrowing screen | 3 days | Sat 9/15/12 | Tue 9/18/12 | LinhLLL, KhanhLTM
3.2.4.2.2 View borrowing screen | 3 days | Tue 9/18/12 | Thu 9/20/12 | LinhLLL, KhanhLTM
3.2.4.1.3 Borrowing screen | 3 days | Thu 9/20/12 | Sun 9/23/12 | LinhLLL, KhanhLTM
3.2.5 Create Report 4 (System design) | 7 days | Mon 9/17/12 | Sun 9/23/12 | TuanNA, LocND
3.2.5.1 Create Database design | 7 days | Mon 9/17/12 | Sun 9/23/12 | TuanNA
3.2.5.2 Create System design | 7 days | Mon 9/17/12 | Sun 9/23/12 | LocND
3.2.6 Coding | 15 days | Thu 9/20/12 | Thu 10/4/12 | LocND, TuanNA
3.2.6.1 Schedule | 15 days | Thu 9/20/12 | Thu 10/4/12 | LocND
3.2.6.1.1 Input screen | 3 days | Thu 9/20/12 | Sun 9/23/12 | LocND
3.3.6.1.2 Main screen and add new screen | 5 days | Sun 9/23/12 | Fri 9/28/12 | LocND
3.3.6.1.3 View screen | 3 days | Fri 9/28/12 | Sun 9/30/12 | LocND
3.3.6.1.4 Edit screen | 4 days | Sun 9/30/12 | Thu 10/4/12 | LocND
3.2.6.2 Borrowing and Lending | 15 days | Thu 9/20/12 | Thu 10/4/12 | LocND
3.2.6.2.1 Input screen | 3 days | Thu 9/20/12 | Sun 9/23/12 | TuanNA
3.3.6.2.2 Add new screen | 5 days | Sun 9/23/12 | Fri 9/28/12 | TuanNA
3.3.6.2.3 View detail screen | 3 days | Fri 9/28/12 | Sun 9/30/12 | TuanNA
3.3.6.2.4 Edit screen | 4 days | Sun 9/30/12 | Thu 10/4/12 | TuanNA
3.3.6.2.5 Intergrate Schedule and Borrowing & Lending function | 1 day | Thu 10/4/12 | Thu 10/4/12 | LocND, TuanNA
3.2.7 Summit and Review | 0 day | Mon 9/24/12 | Mon 9/24/12
3.2.7.1 Use case diagram | 0 day | Mon 9/24/12 | Mon 9/24/12 | Mr. HienNV, PFM Team
3.2.7.2 Report 1 (ver 0.1) | 0 day | Mon 9/24/12 | Mon 9/24/12 | Mr. HienNV, PFM Team
3.2.7.3 System design | 0 day | Mon 9/24/12 | Mon 9/24/12 | Mr. HienNV, PFM Team
3.2.7.4 Database design | 0 day | Mon 9/24/12 | Mon 9/24/12 | Mr. HienNV, PFM Team
3.2.7.4 Final GUI(ver 0.1) | 0 day | Mon 9/24/12 | Mon 9/24/12 | Mr. HienNV, PFM Team
3.2.7.5 Schedule funtion ( Input screen) | 0 day | Mon 9/24/12 | Mon 9/24/12 | Mr. HienNV, PFM Team
3.2.7.6 Borrowing and Lending function (Input screen) | 0 day | Mon 9/24/12 | Mon 9/24/12 | Mr. HienNV, PFM Team
3.2.8 Update Report 1 | 7 days | Mon 9/24/12 | Mon 10/1/12 | GamNT
3.2.9 Update SRS | 7 days | Mon 9/24/12 | Mon 10/1/12 | GamNT, LinhLLL
3.2.10 Update Final GUI ( release) | 7 days | Mon 9/24/12 | Mon 10/1/12 | LinhLLL
3.2.11 Update System design | 7 days | Mon 9/24/12 | Mon 10/1/12 | LocND, TuanNA
3.2.11.1 Update Database design | 7 days | Mon 9/24/12 | Mon 10/1/12 | TuanNA
3.2.11.2 Update System design | 7 days | Mon 9/24/12 | Mon 10/1/12 | LocND
3.2.11.3 Create detail database design | 7 days | Mon 9/24/12 | Mon 10/1/12 | TuanNA
3.2.11.4 Create detail system design | 7 days | Mon 9/24/12 | Mon 10/1/12 | LocND
3.2.12 Prepare slide for the project assessment | 1 day | Tue 9/25/12 | Tue 9/25/12 | LinhLLL, TuanNA
3.2.13 Create testcase for Schedule, Borrowing and Lending function | 2 days | Thu 9/27/12 | Sat 9/29/12 | KhanhLTM
3.2.14 Research | 2 days | Wed 9/26/12 | Thu 9/27/12 | LocND
3.2.14.1 QR code | 1 day | Wed 9/26/12 | Wed 9/26/12 | LocND
3.2.14.2 NFC code | 1 day | Thu 9/27/12 | Thu 9/27/12 | LocND
3.2.15 Create research report | 2 days | Wed 9/26/12 | Thu 9/27/12 | LocND
3.2.16 Create detail function information document | 1 day | Thu 9/27/12 | Thu 9/27/12 | GamNT
3.2.17 Release Schedule, Borrowing and Lending function | 0 day | Wed 10/3/12 | Wed 10/3/12 | LocND,TuanNA
3.2.18 Execute test | 1 days | Wed 10/3/12 | Thu 10/4/12 | KhanhLTM, LinhLLL, GamNT
3.2.19 Complete test round 1 | 0 day | Thu 10/4/12 | Thu 10/4/12 | KhanhLTM, LinhLLL, GamNT
3.2.20 Fix bugs of Schedule, Borrowing and Lending function | 3 day | Thu 10/4/12 | Sat 10/6/12 | TuanNA, LocND
3.2.21 Execute test round 2 | 1 day | Sat 10/6/12 | Sun 10/7/12 | KhanhLTM, LinhLLL, GamNT
3.2.22 Create report 2 (Plan) | 5 days | Mon 10/1/12 | Fri 10/5/12 | GamNT
3.2.23 Review Schedule, Borrowing and Lending function | 0 day | Mon 10/8/12 | Mon 10/8/12 | Mr HienNV, PFM Team
3.2.23.1 Schedule function (all screen) | 0 day | Mon 10/8/12 | Mon 10/8/12 | Mr HienNV, PFM Team
3.2.23.2 Borrowing and Lending function (all screen) | 0 day | Mon 10/8/12 | Mon 10/8/12 | Mr HienNV, PFM Team
3.2.23.3 Intergrate Schedule and Borrowing & Lending function | 0 day | Mon 10/8/12 | Mon 10/8/12 | Mr HienNV, PFM Team
3.2.23.4 GUI | 0 day | Mon 10/8/12 | Mon 10/8/12 | Mr HienNV, PFM Team
3.2.23.3 Report 2 | 0 day | Mon 10/8/12 | Mon 10/8/12 | Mr HienNV, PFM Team
3.2.24 Meeting for complete sprint 1 | 0 day | Mon 10/8/12 | Mon 10/8/12 | Mr HienNV, PFM Team
3.3 Sprint 2 ( Income and Expense management, Warning function) | 12 days | Mon 10/8/12 | Sat 10/20/12
3.3.1 Update Use case | 2 days | Mon 10/8/12 | Wed 10/10/12 | LinhLLL
3.3.2 Create GUI for Sprint 2 (ver 0.1) | 4 days | Mon 10/8/12 | Fri 10/12/12 | LinhLLL
3.3.2.1 Income and Expense management | 3 days | Mon 10/8/12 | Thu 10/11/12 | LinhLLL
3.3.2.1 Main screen | 1 day | Mon 10/8/12 | Tue 10/9/12 | LinhLLL
3.3.2.2 View detail income and expense screen | 1 day | Tue 10/9/12 | Wed 10/10/12 | LinhLLL
3.3.2.3 Input income or expense screen | 1 day | Wed 10/10/12 | Thu 10/11/12 | LinhLLL
3.3.2.4 Edit income or expense screen | 1 day | Thu 10/11/12 | Fri 10/12/12 | LinhLLL
3.3.2.2 Warning, Report | 3 days | Tue 10/9/12 | Fri 10/12/12 | LinhLLL
3.3.2.2.1 Set up warning screen | 1 day | Tue 10/9/12 | Wed 10/10/12 | LinhLLL
3.3.2.2.2 Report screen | 2 days | Wed 10/10/12 | Fri 10/12/12 | LinhLLL
3.3.3 Update System design | 5 days | Mon 10/8/12 | Thu 10/13/12 | LocND, TuanNA
3.3.4 Update report 2 ( Plan) | 7 days | Mon 10/8/12 | Mon 10/15/12 | PFM Team
3.3.5 Coding | 7 days | Mon 10/8/12 | Mon 10/15/12 | LocND
3.3.5.1 Income and Expense management | 7 days | Mon 10/8/12 | Mon 10/15/12 | LocND
3.3.5.2 Warning | 7 days | Mon 10/8/12 | Mon 10/15/12 | LocND
3.3.6 Create test case for sprint 2 | 3 days | Wed 10/11/12 | Sun 10/14/12 | KhanhLTM
3.3.7 Research chart engine for report function | 10 days | Mon 10/8/12 | Thu 10/18/12 | TuanNA
3.3.7 Summit and Review | 0 day | Mon 10/15/12 | Mon 10/15/12 | Mr. HienNV, PFM Team
3.3.7.1 Report 2 | 0 day | Mon 10/15/12 | Mon 10/15/12 | Mr. HienNV, PFM Team
3.3.7.2 Coding ( All functions) | 0 day | Mon 10/15/12 | Mon 10/15/12 | Mr. HienNV, PFM Team
3.3.7.3 GUI | 0 day | Mon 10/15/12 | Mon 10/15/12 | Mr. HienNV, PFM Team
3.3.7.4 System design | 0 day | Mon 10/15/12 | Mon 10/15/12 | Mr. HienNV, PFM Team
3.3.8 Update GUI (final) | 1 day | Mon 10/15/12 | Tue 10/16/12 | LinhLLL
3.3.9 Execute test round 1 | 1 day | Mon 10/15/12 | Tue 10/16/12 | KhanhLTM, LinhLLL, GamNT
3.3.10 Fix bugs | 2 days | Tue 10/16/12 | Thu 10/18/12 | LocND
3.3.11 Execute test round 2 | 1 day | Thu 10/18/12 | Fri 10/19/12 | KhanhLTM, LinhLLL, GamNT
3.3.12 Release final build version | 1 day | Fri 10/19/12 | Sat 10/20/12 | LocND
3.3.12 Review Income and Expense management, Warning functions | 0 day | Sat 10/20/12 | Sat 10/20/12 | Mr. HienNV, PFM Team
3.3.13 Meeting for complete sprint 2 | 0 day | Sat 10/20/12 | Sat 10/20/12 | Mr. HienNV, PFM Team
3.4 Sprint 3 ( NFC and QR Code) | 12 days | Sat 10/20/12 | Thu 11/1/12
3.3.1 Update Use case | 1 day | Sat 10/20/12 | Sun 10/21/12 | LinhLLL
3.3.2 Create GUI (ver 0.1) | 2 days | Sat 10/20/12 | Mon 10/22/12 | LinhLLL
3.3.2.1 NFC | 2 days | Sat 10/20/12 | Mon 10/22/12 | LinhLLL
3.3.2.2 QR code | 2 days | Sat 10/20/12 | Mon 10/22/12 | LinhLLL
3.3.3 Update System design | 2 days | Sat 10/20/12 | Mon 10/22/12 | LocND, TuanNA
3.3.4 Update report 2 ( Plan) | 2 days | Sat 10/20/12 | Mon 10/22/12 | LinhLLL, GamNT
3.3.5 Coding | 16 days | Sat 10/20/12 | Mon 11/5/12 | LocND, TuanNA
3.3.5.1 Use QR code to input expense | 16 days | Sat 10/20/12 | Mon 11/5/12 | TuanNA
3.3.5.2 Use NFC to input expense | 16 days | Sat 10/20/12 | Mon 11/5/12 | LocND
3.3.6 Create test case for sprint 3 | 3 days | Sat 10/20/12 | Tue 10/23/12 | KhanhLTM
3.3.7 Summit and Review | 0 day | Mon 11/5/12 | Mon 11/5/13 | Mr. HienNV, PFM Team
3.3.7.1 Report 2 (final) | 0 day | Mon 11/5/12 | Mon 11/5/12 | Mr. HienNV, PFM Team
3.3.7.2 Coding | 0 day | Mon 11/5/12 | Mon 11/5/12 | Mr. HienNV, PFM Team
3.3.7.3 GUI | 0 day | Mon 11/5/12 | Mon 11/5/12 | Mr. HienNV, PFM Team
3.3.7.4 Test case | 0 day | Mon 11/5/12 | Mon 11/5/12 | Mr. HienNV, PFM Team
3.3.8 Execute test round 1 | 1 day | Mon 11/5/12 | Tue 11/6/12 | KhanhLTM, LinhLLL, GamNT
3.3.9 Fix bugs | 1 days | Tue 11/6/12 | Tue 11/6/12 | LocND, TuanNA
3.3.10 Execute test round 2 | 1 day | Tue 11/6/12 | Tue 11/6/12 | KhanhLTM, LinhLLL, GamNT
3.3.11 Summit and review | 0 day | Thu 11/8/12 | Thu 11/8/12 | Mr. HienNV, PFM Team
3.3.11.1 Review NFC and QR code | 0 day | Thu 11/8/12 | Thu 11/8/12 | Mr. HienNV, PFM Team
3.3.12 Meeting for complete sprint 3 | 0 day | Thu 11/8/12 | Thu 11/8/12 | Mr. HienNV, PFM Team
3.4 Sprint 4 ( Synchronize function & Report function) | 10 days | Thu 11/8/12 | Sun 11/18/12
3.4.1 Update Use case | 2 days | Thu 11/8/12 | Sat 11/10/12 | LinhLLL
3.4.2 Create GUI of Synchronize function (ver 0.1) | 1 day | Thu 11/8/12 | Fri 11/9/12 | LinhLLL
3.4.3 Update System design | 3 days | Thu 11/8/12 | Sun 11/11/12 | LocND, TuanNA
3.4.4 Update SRS(ver 0.2) | 3 days | Thu 11/8/12 | Sun 11/11/12 | GamNT, LinhLLL
3.4.5 Coding | 7 days | Thu 11/8/12 | Thu 11/15/12 | LocND, TuanNA
3.4.5.1 Synchronize function | 7 days | Thu 11/8/12 | Thu 11/15/12 | LocND
3.4.5.2 Report function | 7 days | Thu 11/8/12 | Thu 11/15/12 | TuanNA
3.4.6 Create test case for sprint 4 | 3 days | Thu 11/8/12 | Sun 11/11/12 | KhanhLTM
3.4.7 Summit and Review | 0 day | Mon 11/12/12 | Mon 11/12/12 | Mr. HienNV, PFM Team
3.4.7.1 Report 3 (ver 0.1) | 0 day | Mon 11/12/12 | Mon 11/12/12 | Mr. HienNV, PFM Team
3.4.7.2 Coding | 0 day | Mon 11/12/12 | Mon 11/12/12 | Mr. HienNV, PFM Team
3.4.7.3 GUI | 0 day | Mon 11/12/12 | Mon 11/12/12 | Mr. HienNV, PFM Team
3.4.7.4 Test case | 0 day | Mon 11/12/12 | Mon 11/12/12 | Mr. HienNV, PFM Team
3.4.8 Execute test round 1 | 1 day | Thu 11/15/12 | Fri 11/16/12 | KhanhLTM, LinhLLL, GamNT
3.4.9 Fix bugs | 1 day | Fri 11/16/12 | Sat 11/17/12 | LocND, TuanNA
3.4.10 Execute test round 2 | 1 day | Sat 11/17/12 | Sun 11/18/12 | KhanhLTM, LinhLLL, GamNT
3.4.11 Summit and review | 0 day | Sun 11/18/12 | Sun 11/18/12 | Mr. HienNV, PFM Team
3.4.11.1 Synchronize function | 0 day | Sun 11/18/12 | Sun 11/18/12 | Mr. HienNV, PFM Team
3.4.12 Meeting for complete sprint 4 | 0 day | Sun 11/18/12 | Sun 11/18/12 | Mr. HienNV, PFM Team
4. Sprint 5 (Import & export fuction) | 11 days | Sun 11/18/12 | Thu 11/29/12
4.1 Create final GUI of application | 5 days | Sun 11/18/12 | Fri 11/23/12 | LinhLLL
4.2 Update report 3 (ver 0.1) | 3 days | Sun 11/18/12 | Tue 11/20/12 | GamNT
4.3 Coding | 10 days | Sun 11/18/12 | Wed 11/28/12 | LocND, TuanNA
4.3.1 Update code of report function | 10 days | Sun 11/18/12 | Wed 11/28/12 | TuanNA
4.3.2 Import and export function | 5 days | Sun 11/18/12 | Fri 11/23/12 | LocND
4.4 Create test case for sprint 5 | 6 days | Sun 11/18/12 | Sat 11/24/12 | KhanhLTM
4.5 Execute test round 1 | 1 day | Sat 11/24/12 | Sun 11/25/12 | KhanhLTM, LinhLLL, GamNT
4.6 Fix bugs | 2 day | Sun 11/25/12 | Tue 11/27/12 | LocND, TuanNA
4.7 Execute test round 2 | 1 day | Tue 11/27/12 | Wed 11/28/12 | KhanhLTM, LinhLLL, GamNT
4.8 Summit and review | 0 day | Thu 11/29/12 | Thu 11/29/12 | Mr. HienNV, PFM Team
4.8.1 Final GUI | 0 day | Thu 11/29/12 | Thu 11/29/12 | Mr. HienNV, PFM Team
4.8.2 Import and export function | 0 day | Thu 11/29/12 | Thu 11/29/12 | Mr. HienNV, PFM Team
5. System implement | 5 days | Thu 11/29/12 | Tue 12/4/12
4.1 Intergrate 4 main functions | 5 days | Thu 11/29/12 | Tue 12/4/12 | LocND, TuanNA
4.2 Update code of report function | 5 days | Thu 11/29/12 | Tue 12/4/12 | TuanNA
4.3 Update report 3 (ver 0.2) | 3 days | Thu 11/29/12 | Sun 12/2/12 | GamNT, LinhLLL
4.4 Create report 5 | 5 days | Thu 11/29/12 | Tue 12/4/12 | KhanhLTM
4.5 Create report 4 (ver 0.1) | 5 days | Thu 11/29/12 | Tue 12/4/12 | LocND, TuanNA
4.6 Update final GUI (ver 0.1) | 5 days | Thu 11/29/12 | Tue 12/4/12 | LinhLLL, KhanhLTM
4.7 Summit and review | 0 day | Tue 12/4/12 | Tue 12/4/12 | Mr. HienNV, PFM Team
4.7.1 Coding | 0 day | Tue 12/4/12 | Tue 12/4/12 | Mr. HienNV, PFM Team
4.7.2 Report 3 | 0 day | Tue 12/4/12 | Tue 12/4/12 | Mr. HienNV, PFM Team
4.7.3 Report 4 | 0 day | Tue 12/4/12 | Tue 12/4/12 | Mr. HienNV, PFM Team
5. System test | 7 days | Tue 12/4/12 | Tue 12/11/12
5.1 Update final GUI (ver 0.2) | 5 days | Tue 12/4/12 | Sun 12/9/12 | LinhLLL
5.2 Update report 4 (ver 0.2) | 3 days | Tue 12/4/12 | Fri 11/7/12 | LocND, TuanNA
5.3 Prepare document for closing project | 7 days | Tue 12/4/12 | Tue12/11/12 | PFM Team
5.3.1 Update report 5 (ver 0.1) | 2 days | Tue 12/4/12 | Thu 12/6/12 | KhanhLTM
5.3.2 Update report 4 (final) | 5 days | Tue 12/4/12 | Sun 12/9/12 | LocND, TuanNA
5.3.3 Create final report | 5 days | Tue 12/4/12 | Sun 12/9/12 | PFM Team
5.3.4 Create User Manual Document | 6 days | Tue 12/4/12 | Mon 12/10/12 | PFM Team
5.4 Summit and review | 0 day | Tue 12/11/12 | Tue 12/11/12 | Mr. HienNV, PFM Team
5.4.1 Report 4 | 0 day | Tue 12/11/12 | Tue 12/11/12 | Mr. HienNV, PFM Team
5.4.2 Report 5 | 0 day | Tue 12/11/12 | Tue 12/11/12 | Mr. HienNV, PFM Team
5.4.3 Final report | 0 day | Tue 12/11/12 | Tue 12/11/12 | Mr. HienNV, PFM Team
5.4.4 User manual | 0 day | Tue 12/11/12 | Tue 12/11/12 | Mr. HienNV, PFM Team
5.4.5 Final GUI | 0 day | Tue 12/11/12 | Tue 12/11/12 | Mr. HienNV, PFM Team
6. Closing | 10 days | Tue 12/11/12 | Fri 12/21/12
6.1 Prepare project presentation | 7 days | Tue 12/11/12 | Tue 12/18/12 | PFM Team
6.2 Complete final report | 7 days | Tue 12/11/12 | Tue 12/18/12 | GamNT
6.3 Complete project presentation | 2 days | Tue 12/11/12 | Thu 12/20/12 | LinhLLL
6.4 Release final report & project code | 0 day | Tue 12/11/12 | Tue 12/18/12 | PFM Team
6.5 Meeting for closing project | 0 day | Tue 12/11/12 | Tue 12/11/12 | Mr. HienNV, PFM Team